## Time Sheet
Day | Work done | Time Spent
31-07-2020

## Requirements
Roles
BASIC TODO | WHAT | Functionality
CRUD in all | All parts of project must have crud |  | Admin | Employee | Client | Viewer
Authentication | login, logout, password reset and recover from email | Register |  | X | X | X
Roles | Admin, Employee, Client, Viewer | Login | X | X | X
2 third party controlles | Syncfusion and others | Modify Profile | X | X | X
online and functional | Online and easy to work | Recover Password | X | X | X
no crash |  | Change Password | X | X | X
adapted front end |  | Admin Employees | X
|  | Book Maintenance |  | X | X
|  | Admin Booked Maintenace |  | X | X
|  | Create Car |  | X | X
Milestones |  | Change car |  | X | X
|  | View Basic Information |  | X | X | X
|  | Admin Maintenance | X | X

## WBS
WBS - Projecto oficina
1 | Criar contexto de dados
2 | Criar repositorio generico
| 2.1 | Criar interfaces de acesso ao repositorio generico
| 2.2 | Criar Entidades
| 2.3 | Criar Seed de Base de dados
| 2.4 | Testar integracao e Crud
3 | Criar Users
| 3.1 | Integracao entre as entidades e os users
| 3.2 | Testar integracao das entidades com os Users
4 | Integracao e relacao entre entidades
| 4.1 | validacoes e testes iniciais entre relacoes
5 | Backend
| 5.1 | Recepcao
|  | 5.1.1 | Agendar marcacoes
|  | 5.1.2 | Anular marcacoes
|  | 5.1.3 | Gerir Marcacoes
|  | 5.1.4 | Testes e debug
| 5.2 | Oficina
|  | 5.2.1 | Gerir Reparacoes
|  | 5.2.2 | Concluir Reparacoes
|  | 5.2.3 | Testes e debug
| 5.3 | Facturacao
|  | 5.3.1 | Emitir factura
|  | 5.3.2 | Cobrar factura
|  | 5.3.3 | Testes e debug
| 5.3 | Admin
|  | 5.3.1 | Gerir Users
|  | 5.3.2 | Gerir acesso a aplicacoes internas
|  | 5.3.3 | Gerir info Geral
|  | 5.3.4 | Testes e debug
6 | Frontend
| 6.1 | Utilizadores
|  | 6.1.1 | Acesso a aplicacao / Informacao empresa
|  | 6.1.2 | Registo na aplicacao
|  | 6.1.3 | Agendar marcacoes
|  | 6.1.4 | Cancelar Marcacoes
|  | 6.1.4 | Gerir informacao pessoal
|  | 6.1.5 | Cancelar e gerir registo
7 | Template / Layout
| 7.1 | Integracao do layout na aplicacao
| 7.2 | Testes Finais
8 | Publicacao